## TestScenarios
Project Name | Ghorer Bazar BD
Reference Document | FRS
Created By | Md Abu Sayed Fahim
Creation Date | 20-08-2023
Approval Date | 22-08-2023
Test Scenario ID | Reference | Test Scenario Description | Priority | Number of Test Cases
TS_001 | FRS | Validate the working of Sign up functionality | P0 | 25
TS_002 | FRS | Validate the working of Sign in functionality | P0 | 23
TS_003 | FRS | Validate the working of Logout functionality | P0
TS_004 | FRS | Validate the working of Forgot Password functionality | P2
TS_005 | FRS | Validate the working of OTP functionality | P1 | 3
TS_006 | FRS | Validate the working of Search functionality | P4
TS_007 | FRS | Validate the working of Home Page functionality | P4
TS_008 | FRS | Validate the working of Language functionality | P5
TS_009 | FRS | Validate the working of 'All categories' functionality
TS_010 | FRS | Validate the Product Display Page functionality for the different types of Products
TS_011 | FRS | Validate the working of 'Shopping Cart' functionality
TS_012 | FRS | Validate the working of 'Buy now' functionality
TS_013 | FRS | Validate the working of 'Add Coupon' functionality
TS_014 | FRS | Validate the working of Checkout functionality
TS_015 | FRS | Validate the My Account functionality
TS_016 | FRS | Validate the working of My Account > Dashboard functionality
TS_017 | FRS | Validate the working of My Account > 'Change Password' functionality
TS_018 | FRS | Validate the working of My Account > 'Support' functionality
TS_019 | FRS | Validate the working of My Account > 'My wallet' functionality
TS_020 | FRS | Validate the working of My Account > 'My points' functionality
TS_021 | FRS | Validate the working of My Orders > 'Order History' functionality
TS_022 | FRS | Validate the working of Footer functionality

## TestCase
Product Name |  | Ghorer Bazar BD | TC Start Date | 2023-05-10 | TC Execution Start Date | - - |  |  |  |  | TEST CASE
Module Name |  | Account | TC End Date | 15/10/2023 | TC Execution End Date | - - |  |  |  |  | PASS | 48
Epic |  |  | Test Case Developed By | Md Abu Sayed Fahim | Browser (tested) | Yes |  |  |  |  | FAIL | 10
Developer Name (TL) |  |  | Test Case Reviewed By | Ehsanul Alam Sabbir | Performance (tested) | Yes |  |  |  |  | NO RUN | 0
Test Executed by | [10 empty] | BLOCKED | 0
[11 empty] | TOTAL | 58
#SL | Module | Type of Testing | Features | Test Cases | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bugs Screen Shot | Dev Comments | Final Status | Remarks
1 |  | Browser Compatibility, Cross browser Testing |  | Verifying that the site runs in different browsers | Should run in different browsers | Found as per expectation | Chrome Internet Explorer Mozilla Firefox Microsoft Edge Opera Mini | 1. Goto different browsers 2. Search 'Ghorer Bazar BD' 3. Goto the website |  |  | Passed
|  |  |  | Checking responsiveness of the site in different browsers | Should be responsive | Found as per expectation | N/A | 1. Goto different browsers 2. Goto the URL https://ghorerbazarbd.com/new/ 3. Check the responsiveness by reizing the browser |  |  | Passed
2 | User Management | UI Testing | Sign Up | Checking spelling or grammatical mistakes | No spelling or grammatical mistakes | Found as per expectation | N/A | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on Signup button at the right corner 3. Check the spelling and grammar of the website |  |  | Passed
3 |  |  |  | Verifying the font, text color and style | Should be as per the requirement | Found as per expectation | N/A | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on Register button at the right corner 3. Check the font, text color and style |  |  | Passed
4 |  |  |  | Verifying mandatory field is marked with a red asterisk | Red asterisk should be present | Not found as per expectation | N/A | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on Register button at the right corner 3. Check red asterisk beside mandatory field | Red asterisk error |  | Failed
6 |  |  |  | Checking alignment of the fields | Proper alignment of the fields should be present | Found as per expectation | N/A | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on Register button at the right corner 3. Check alignment of the fields |  |  | Passed
|  |  |  | Checking all options are in right position | Should be enough gap between options | Back to login' option close to another option | N/A | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click signup from the right corner 3. Check all options are in right position | Back to login position |  | Failed
10 |  | Functional Testing |  | Checking the cusrsor automatically on the field | Should be on the field | Not showing the cursor as expected place | N/A | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on signup button at the right corner 3.Check cursor's position | N/A |  | Failed
12 |  |  |  | Signing up with empty fields shows warning | Should show warning | Found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Input space at first position of firstname and lastname |  |  | Passed
14 |  |  |  | Checking alert message for all mandatory fields | Should pop up an error message | Found as per expectation | N/A | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on Signup button at the right corner 3. Keeping blank in each field and checking repeatedly |  |  | Passed
15 |  |  |  | Inputing name with numbers & special characters | Should not accept the provided input | Not found as per expectation | $$%$$ @@$$& | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on Signup button at the right corner 3. Enter numbers & special characters in name |  |  | Failed
18 |  |  |  | Inputing name with alphanumeric characters | Should accept the provided input | Found as per expectation | Sayed123 Fahim321 | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on Signup button at the right corner 3. Enter alphanumeric characters in name |  |  | Passed
19 |  |  |  | Inputing name with alphabets | Should accept the provided input | Found as per expectation | Sayed Fahim | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on Signup button at the right corner 3. Enter alphabets in name |  |  | Passed
20 |  |  |  | Entering comma between alphabets for name | Should not accept the provided input | Not found as per expectation | Sa,,yed F,a,h,im | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on Signup button at the right corner 3. Enter comma between alphabets | Comma error |  | Failed
21 |  |  |  | Entering space between alphabets for name | Should accept the provided input | Found as per expectation | Sayed Fahim Fahim Sayed | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on Signup button at the right corner 3. Enter space between alphabets in name |  |  | Passed
23 |  |  |  | Checking by inputing registered email | Should not allow user to register and display a pop message | Found as per expectation with an error message | sayedfahim@gmail.com | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on Signup button at the right corner 3. Fill the email address with already registered email |  |  | Passed
24 |  |  |  | Checking by inputing invalid email format | Should not accept the provided input and display an error message | Found as per expectation with an error message | .ss..ss@gmail.com | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on Signup button at the right corner 3. Fill the email address with invalid email address format |  |  | Passed
25 |  |  |  | Checking by inputing valid email format | Should accept the provided input | Found as per expectation | sayedfahim@gmail.com | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on Signup button at the right corner 3. Fill the email address with valid email address format |  |  | Passed
|  |  |  | Checking by inputing invalid phone number | Should not accept the provided input | Found as per expectation | 121245780000 | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on Signup button at the right corner 3. Input invalid phone number |  |  | Passed
|  |  |  | Checking by inputing valid phone number | Should accept the provided input | Found as per expectation | 01580367043 | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on Signup button at the right corner 3. Input valid phone number |  |  | Passed
26 |  |  |  | Checking password values are masked | Should be masked | Found as per expectation | 123456 | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on Signup button at the right corner 3. Enter password |  |  | Passed
31 |  |  |  | Checking by inputing weak password | Should not allow user to register & show a alert for a better password | Not found as per expectation | 123 | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on Signup button at the right corner 3. Enterweak password | N/A |  | Failed
|  |  |  | Checking by inputing Strong password | Should allow user to register | Found as per expectation | $&abc#cba | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on Signup button at the right corner 3. Enter strong password |  |  | Passed
32 |  |  |  | Inputing valid data for password | Should allow user to register | Found as per expectation | sayed@2023 | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on Signup button at the right corner 3. Enter valid password |  |  | Passed
45 |  |  |  | Checking confirmation mail sent to the newly registered email | Sent successfully | No confirmation email is sent | Name: Sayed Email: Sayedfahim713@gmail.com Password: sayed@2023 | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on Signup button at the right corner 3. Fill all the fiels with valid credentials 4.Click 'Signup with Password' 5. Check mail and confirm account | Confirmation email error |  | Failed
|  |  |  | Checking if 'Signup with password' button working | Should function the button | Found as per expectation | N/A | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on Signup button at the right corner 3. Click on 'Sign up with password' |  |  | Passed
|  |  |  | Checking if 'Signup with OTP' button working | Should function the button | Found as per expectation | N/A | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on Signup button at the right corner 3. Click on 'Sign up with OTP' |  |  | Passed
|  |  |  | Checking 'Signup with OTP' functionality | Should work properly by sending OTP | Found as per expectation | N/A | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on Signup button at the right corner 3. Click on 'Sign up with OTP' 4. Check OTP received or not | N/A |  | Passed
|  |  |  | Checking by clicking the resend button | Should function correctly | Functioning successfully | N/A | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on Signup button at the right corner 3. Click on resend 4. Check OTP received or not |  |  | Passed
|  |  |  | Checking by resending the OTP | Should resend OTP | Found as per expectation | N/A | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on Signup button at the right corner 3. Click on resend 4. Check OTP received or not | N/A |  | Passed
Passed
48 |  | Usability Testing |  | Checking copy paste functionality in every field | Should copy and paste text from fields | Functioning successfully | sayed123 | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on Signup button at the right corner 3. Copy paste text in every field |  |  | Passed
49 |  |  |  | Checking keyboard tab button functionality | Should switch to another field and highlight text | Functioning successfully | Enter tab in every field | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on Signup button at the right corner 3. Enter tab in every field |  |  | Passed
50 |  |  |  | Checking keyboard enter button functionality | Should switch to another field | Functioning successfully | Input Enter in every field | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on Signup button at the right corner 3. Enter enter in every field |  |  | Passed
Passed
51 |  | UI Testing Functionality Testing | Sign In | Checking the log in screen will appear after clicking on user account | Should appear log in screen | Found as per expectation | N/A | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on account button at the right corner 3. Check login screen appear |  |  | Passed
|  |  |  | Checking all login-related elements and fields are present on the log in screen | Should be present | Found as per expectation |  | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on account button at the right corner 3.Checking all the login related fields. |  |  | Passed
|  |  |  | Checking the size, color, and UI of different elements should match the specifications. | Should match the specifications | Found as per expectation |  | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on account button at the right corner 3. Checking Size, color and UI |  |  | Passed
|  |  |  | Checking the availability of checkbox with the label remember password | Should be a checkbox beside remember password | No checkbox is found | N/A | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on account button at the right corner 3. Checking the checkbox | No checkbox error |  | Failed
|  |  |  | Checking whether an eye icon is added to the password field or not. | Should be an eye icon | No eye icon is found | N/A | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on account button at the right corner 3. Checking the eye icon | No eye icon error |  | Failed
|  | Functionality Testing |  | Checking by Keeping email and password field blank | Should not allow user to log in and display an error messeage | Found as per expectation | N/A | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on account button at the right corner 3 Keep both the fields blank |  |  | Passed
|  |  |  | Checking by inputing email that is not registered before | Should not allow user to login and display an error messeage | Found as per expectation | asayedfahim03@gmail.com | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on account button at the right corner 3. Input email that isnt registered before |  |  | Passed
52 |  |  |  | Checking by inputing registered email | Should allow user to log in | Found as per expectation | sayedfahim@gmail.com | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button at the right corner 3. Input values in password field and check if it is masked |  |  | Passed
|  |  |  | Checking the password is masked or not | Should be masked | Found as per expectation | 12345 | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on account button at the right corner 3.Input values in password field and check if it is masked |  |  | Passed
|  |  |  | Checking with invalid password | Should not allow user to log in and display an error messeage | Found as per expectation | ….. | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on account button at the right corner 3. Input invalid password. |  |  | Passed
|  |  |  | Checking with valid password | Should allow user to login | Found as per expectation | 12345 | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on account button at the right corner 3. Input valid password |  |  | Passed
54 |  |  |  | Checking login valid credentials in email and password field | Should allow user to login | Found as per expectation | Email: sayedfahim@gmail.com Password: 12345 | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on account button at the right corner 3. Input valid credentials in email and password field |  |  | Passed
55 |  |  |  | Checking ‘Forgot your Password?’ functionality | Should sent an email for recovering password | Found as per expectation | N/A | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on account button at the right corner 3.Click on 'Forgot Password' 4. Check email |  |  | Passed
57 |  |  |  | Verifying change the password link is sent to valid email address | Should be sent to valid email address | Found as per expectation | N/A | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on account button at the right corner 3.Click on 'Forgot Password' 4. Check the registered email |  |  | Passed
58 |  |  |  | Checking the link for changing password working | New link should work | Found as per expectation | N/A | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on account button at the right corner 3.Goto the mail 4. Check the link working or not |  |  | Passed
|  |  |  | Checking by inputing different data in password & confirm password | Should not change password & display an error messege | Found as per expectation | Password: 12345 Confirm Password: 54321 | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on account button at the right corner 3. Goto mail 4. Click the link 5. Input different data in pass and confirm pass field |  |  | Passed
59 |  |  |  | Checking by inputing same data in password & confirm password | Should change the password | Password not changing & showing 'invalid credentials' | Password: 12345 Confirm Password: 12345 | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on account button at the right corner 3. Goto mail 4. Click the link 5. Input same data in pass and confirm pass field | Password not changing error |  | Failed
|  |  |  | Checking with invalid phone number | Should not allow user to log in and display an error messeage | Found as per expectation | 0158036704343 | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on account button at the right corner 3. Input invalid number |  |  | Passed
|  |  |  | Checking with phone number that is not registered before | Should not allow user to log in and display an error messeage | Found as per expectation | 01580367043 | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on account button at the right corner 3. Input number that isnt registered |  |  | Passed
|  |  |  | Checking with registered phone number | Should allow user to login | Found as per expectation | 01985445740 | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on account button at the right corner 3. Input registered number |  |  | Passed
|  |  |  | Checking login with OTP button working or not | The button should function properly | Found as per expectation | N/A | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on account button at the right corner 3. Click on the login with OTP button |  |  | Passed
|  |  |  | Checking login with OTP functioning correctly | Should function correctly by sending OTP | Found as per expectation | N/A | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on account button at the right corner 3. Click on the login with OTP button 4. Check OTP coming or not |  |  | Passed
|  |  |  | Checking by clicking resend option | Should work by resending OTP | Found as per expectation | N/A | 1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on account button at the right corner 3. Click login with OTP button 4. Click resend |  |  | Passed
Negative test
mmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmm

## Bug Report
Bug Reporting
# SL 01
Issue: Red asterisk is not found beside mandatory field
Reproducing Steps:
1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on Register button at the right corner 3. Check red asterisk beside mandatory field
Env: Production.
Module: Signup
Priority: High ¦ Medium ¦ Low
Severity: Blocker ¦ Critical ¦ Major ¦ Minor
Screenshot: Red asteriok error
Expected result: Red asterisk should be present
Responsible QA: Md Abu Sayed Fahim
Bug Reporting
# SL 02
Issue: Back to login position error
Reproducing Steps:
1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click signup from the right corner 3. Check all options are in right position
Env: Production
Module: Signup
Severity: P2
Screenshot: "Back to login position error
Expected result: Back to login button should be in appropriate position
Responsible QA: Md Abu Sayed Fahim
Bug Reporting
# SL 03
Issue: Cursor not showing on the field after clicking on the signup button
Reproducing Steps:
1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on signup button at the right corner 3.Check cursor's position
Env: Production.
Module: Signup
Severity: P2
Screenshot: N/A
Expected result: Cursor should be on the first field after clicking on the signup bitton
Responsible QA: Md Abu Sayed Fahim
Bug Reporting
# SL 04
issue: Accepting name including numbers and special characters
Reproducing Steps:
1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on Signup button at the right corner 3. Enter numbers & special characters in name
Env: Production
Module: Signup
Severity: P1
Screenshot: Wrong input in name error
Expected result: Should not accept any name that including numbers and special characters
Responsible QA: Md Abu Sayed Fahim
Bug Reporting
# SL 05
issue: Comma should not be expected between the name field.
Reproducing Steps:
1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on Signup button at the right corner 3. Enter comma between alphabets
Env: Production
Module: Signup
Severity: P1
Screenshot: Comma error
Expected result: Should not accept any name that including comma
Responsible QA: Md Abu Sayed Fahim
Bug Reporting
# SL 06
issue: Accepting weak password
Reproducing Steps:
1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on Signup button at the right corner 3. Enter weak password
Env: Production
Module: Signup
Severity: P1
Screenshot: N/A
Expected result: Should not accept weak passwords
Responsible QA: Md Abu Sayed Fahim
Bug Reporting
# SL 07
issue: No confirmation email sent to the newly registered email
Reproducing Steps:
1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on Signup button at the right corner 3. Fill all the fiels with valid credentials 4.Click 'Signup with Password' 5. Check gmail for the confirmation
Env: Production
Module: Signup
Severity: P0
Screenshot: Confirmation email error
Expected result: Newly registered email should receive a confirmation email
Responsible QA: Md Abu Sayed Fahim
Bug Reporting
# SL 08
issue: No checkbox is found beside remember me
Reproducing Steps:
1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on account button at the right corner 3. Checking the checkbox
Env: Production
Module: Login
Severity: P0
Screenshot: No checkbox error
Expected result: Should a checkbox beside remember me
Responsible QA: Md Abu Sayed Fahim
Bug Reporting
# SL 09
issue: No eye icon is found beside password field
Reproducing Steps:
1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on account button at the right corner 3. Checking the eye icon
Env: Production
Module: Login
Severity: P2
Screenshot: No eye icon error
Expected result: Should be a eye icon beside password field
Responsible QA: Md Abu Sayed Fahim
Bug Reporting
# SL 10
issue: Password not changing error
Reproducing Steps:
1. Goto the URL https://ghorerbazarbd.com/new/ 2. Click on account button at the right corner 3. Goto mail 4. Click the link 5. Input same data in pass and confirm pass field
Env: Production
Module: Login
Severity: P1
Screenshot: Password not changing error
Expected result: Should change the password into new password
Responsible QA: Md Abu Sayed Fahim

## Test Summary Report
Test Case Report | [6 empty] | Result :
Project Name | Ghorer Bazar BD
Module Name | Account. |  |  |  |  | Total No. | Status
Feature Name | Register Account & Account Login.
Test Case Version | 1 |  |  |  |  | 48 | PASS
Written By | Md Abu Sayed Fahim |  |  |  |  | 10 | FAIL
Executed By | Md Abu Sayed Fahim |  |  |  |  | 0 | Not Executed | New Features:- | Testing Scope:- | Testing Environment :Google Chrome Browser
Reviewed By | Ehsanul Alam Sabbir |  |  |  |  | 0 | Out of Scope
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 48 | 10 | 0 | 0 | 58
Grand Total | 48 | 10 | 0 | 0 | 58
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Test Metrics
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (58/58)*100 = 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/58)*100 = 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (48/58)*100 = 83%
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (10/58)*100 = 17%
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/58)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A

## Recommandation
GENERAL INFORMATION
test stage | Unit performance | Functionality Regression | Integration Acceptance | System Pilot | Interface
Specify the testing stage for this test case
Date: | mm/dd/yy |  | System Date,If Applicable |  | mm/dd/yy
Tester: | Specify the name (s)of who is testing this case scenario. |  | Test Case Number |  | Specify the unique test number assigned to the test case
Test case Description: | Provide a brief description of what functionality the test case
Results: | Pass Fail |  | Incident Number,If Applicable: |  | Specify the unique identifier assingned to the incident.
INTRODUCTION
Requirement(s) to be tested: | Identify the requirments to be tested and include the requirment number and description from the Requirments Traceability Matrix
Roles and Responsibilites: | Describe each project team member and stakeholder involved in the test, and identify their associated responsibility for ensuring the test is executed appropriately
Set Up procedures: | Describe the sequence of actions necessary to prepare for execution of the test
Stop Procedures: | Describe the sequence of actions necessary to terminate the test
ENVIRONMENTAL NEEDS
Hardware: | Identify the qualities and configurations of the hardware required to execute the test case
Software: | Identify system and application software required to execute the test case.Specify any software that the test case will interact with.
Procedural Requirments: | Describe any constraints on the test procedures necessary to execute the test case
TEST
Test Items and Features: | Identify and describe the items and features that will be exercised by the test case.Group the test cases into logically related scenarios that test related items and features.For each item or feature,a reference to its associated requirment source should be include.
Input Specifications: | Define each input required to execute the test case and reference any required relationship between inputs.
Procedural Steps: | Describe the sequence of actions necessary to prepare and execute the test case.Provide detailed testprocedures for each test case; explain precisely how each test case will be executed.
Expected Results of Case: | Describe the outcome anticipated from the test case.Specify the criteria to be used to determine whether the item has passed or failed.
ACTUAL RESULTS
Output Specifications: | Define all of the outputs and features required of the test case and provided expected values. While executing the test, record and describe the visually observable outputs as they occure.Produce tangible evedence of the output such as ascreen print. At the conclusion,discreancies between the expected results and the actual results.